## Sheet1
work_manager_task_unplanned_cou | sequence_number | owner | project_id | project_code | start_date | wbs_id | activity_id | project | monte_carlo_scenario | activity | activity_uncertainty_id | update_date | calendar_name | percent_complete_weighted_by | actual_duration | remaining_duration | planned_duration | record_count | planned_labor_units | actual_labor_units | remaining_labor_units | scope_percent_complete | performance_percent_complete | critical | starred | schedule_percent_complete | remaining_start | planned_start | remaining_late_start | at_completion_duration | units_percent_complete | activity_name | cost_performance_index_labor_un | earned_value_cost | planned_value_cost | schedule_variance | planned_expense_cost | actual_this_period_labor_cost_p | planned_labor_cost | planned_labor_cost_project | planned_material_cost | planned_material_cost_project | planned_non_labor_cost | planned_non_labor_cost_project | planned_total_cost | planned_total_cost_project | remaining_expense_cost | remaining_labor_cost | remaining_labor_cost_project | remaining_material_cost | remaining_material_cost_project | remaining_non_labor_cost | remaining_non_labor_cost_projec | remaining_total_cost | remaining_total_cost_project | actual_expense_cost | actual_labor_cost | actual_labor_cost_project | actual_material_cost | actual_material_cost_project | actual_non_labor_cost | actual_non_labor_cost_project | actual_total_cost | actual_total_cost_project | at_completion_expense_cost | at_completion_labor_cost | at_completion_labor_cost_projec | at_completion_material_cost | at_completion_material_cost_pro | at_completion_non_labor_cost | at_completion_non_labor_cost_pr | at_completion_total_cost | at_completion_total_cost_projec | blplanned_expense_cost | blplanned_labor_cost | blplanned_material_cost | blplanned_non_labor_cost | blplanned_total_cost | accounting_variance | expense_cost_variance | labor_cost_variance | material_cost_variance | non_labor_cost_variance | total_cost_variance | actual_this_period_labor_cost | actual_this_period_non_labor_co | actual_this_period_non_labor__1 | actual_this_period_material_cos | actual_this_period_material_c_1 | actual_this_period_total_cost | actual_this_period_total_cost_p | prior_actual_labor_cost | prior_actual_labor_cost_project | prior_actual_non_labor_cost | prior_actual_non_labor_cost_pro | prior_actual_material_cost | prior_actual_material_cost_proj | prior_actual_total_cost | prior_actual_total_cost_project | budget_at_completion | budget_at_completion_project | planned_value_cost_project | earned_value_cost_project | schedule_variance_project | var_cost | var_cost_project | estimate_to_completion_cost | estimate_to_completion_cost_pro | estimate_at_completion_cost | estimate_at_completion_cost_pro | at_completion_variance | at_completion_variance_project | earned_value_labor_units | schedule_variance_index | cost_variance_labor_units | cost_variance_index | cost_variance_labor_units_index | schedule_performance_index | to_complete_performance_index | driving_path | actual_this_period_non_labor_un | actual_this_period_labor_units | early_start | late_start | secondary_constraint_type | planned_non_labor_units | actual_non_labor_units | remaining_non_labor_units | prior_actual_labor_units | prior_actual_non_labor_units | free_float | total_float | activity_status | percent_complete_type | physical_percent_complete | duration_type | activity_type | activity_priority | at_completion_labor_units | at_completion_non_labor_units | duration_percent_complete | duration_percent_of_planned | labor_units_complete_percent | non_labor_units_complete_percen | activity_percent_complete | remaining_float | activity_work_manager_task_date | activity_work_manager_task_stat | activity_work_manager_task_st_1 | work_manager_task_count | work_manager_task_planned_outsi | work_manager_task_planned_not_c | work_manager_task_planned_compl | program_milestone | at_completion_budget_labor_unit | planned_value_labor_units | schedule_variance_labor_units | schedule_var_index_labor_units | schedule_perf_index_labor_units | cost_performance_index | estimate_to_completion_labor_un | estimate_at_completion_labor_un | variance_at_completion_labor_un | activity_code | finish_date | remaining_finish | planned_finish | remaining_late_finish | early_finish | late_finish | gis_id | resource_code_list | resource_name_list | ls | join_id | Shape__Length | GlobalID
Work Manager Task Unplanned Cou | Sequence Number | Owner | Project ID | Project Code | start_date | wbs_id | activity_id | project | monte_carlo_scenario | activity | activity_uncertainty_id | update_date | calendar_name | percent_complete_weighted_by | actual_duration | remaining_duration | planned_duration | record_count | planned_labor_units | actual_labor_units | remaining_labor_units | scope_percent_complete | performance_percent_complete | critical | starred | schedule_percent_complete | remaining_start | planned_start | remaining_late_start | at_completion_duration | units_percent_complete | activity_name | cost_performance_index_labor_un | earned_value_cost | planned_value_cost | schedule_variance | planned_expense_cost | actual_this_period_labor_cost_p | planned_labor_cost | planned_labor_cost_project | planned_material_cost | planned_material_cost_project | planned_non_labor_cost | planned_non_labor_cost_project | planned_total_cost | planned_total_cost_project | remaining_expense_cost | remaining_labor_cost | remaining_labor_cost_project | remaining_material_cost | remaining_material_cost_project | remaining_non_labor_cost | remaining_non_labor_cost_projec | remaining_total_cost | remaining_total_cost_project | actual_expense_cost | actual_labor_cost | actual_labor_cost_project | actual_material_cost | actual_material_cost_project | actual_non_labor_cost | actual_non_labor_cost_project | actual_total_cost | actual_total_cost_project | at_completion_expense_cost | at_completion_labor_cost | at_completion_labor_cost_projec | at_completion_material_cost | at_completion_material_cost_pro | at_completion_non_labor_cost | at_completion_non_labor_cost_pr | at_completion_total_cost | at_completion_total_cost_projec | blplanned_expense_cost | blplanned_labor_cost | blplanned_material_cost | blplanned_non_labor_cost | blplanned_total_cost | accounting_variance | expense_cost_variance | labor_cost_variance | material_cost_variance | non_labor_cost_variance | total_cost_variance | actual_this_period_labor_cost | actual_this_period_non_labor_co | actual_this_period_non_labor__1 | actual_this_period_material_cos | actual_this_period_material_c_1 | actual_this_period_total_cost | actual_this_period_total_cost_p | prior_actual_labor_cost | prior_actual_labor_cost_project | prior_actual_non_labor_cost | prior_actual_non_labor_cost_pro | prior_actual_material_cost | prior_actual_material_cost_proj | prior_actual_total_cost | prior_actual_total_cost_project | budget_at_completion | budget_at_completion_project | planned_value_cost_project | earned_value_cost_project | schedule_variance_project | var_cost | var_cost_project | estimate_to_completion_cost | estimate_to_completion_cost_pro | estimate_at_completion_cost | estimate_at_completion_cost_pro | at_completion_variance | at_completion_variance_project | earned_value_labor_units | schedule_variance_index | cost_variance_labor_units | cost_variance_index | cost_variance_labor_units_index | schedule_performance_index | to_complete_performance_index | driving_path | actual_this_period_non_labor_un | actual_this_period_labor_units | early_start | late_start | secondary_constraint_type | planned_non_labor_units | actual_non_labor_units | remaining_non_labor_units | prior_actual_labor_units | prior_actual_non_labor_units | free_float | total_float | activity_status | percent_complete_type | physical_percent_complete | duration_type | activity_type | activity_priority | at_completion_labor_units | at_completion_non_labor_units | duration_percent_complete | duration_percent_of_planned | labor_units_complete_percent | non_labor_units_complete_percen | activity_percent_complete | remaining_float | activity_work_manager_task_date | activity_work_manager_task_stat | activity_work_manager_task_st_1 | work_manager_task_count | work_manager_task_planned_outsi | work_manager_task_planned_not_c | work_manager_task_planned_compl | program_milestone | at_completion_budget_labor_unit | planned_value_labor_units | schedule_variance_labor_units | schedule_var_index_labor_units | schedule_perf_index_labor_units | cost_performance_index | estimate_to_completion_labor_un | estimate_at_completion_labor_un | variance_at_completion_labor_un | activity_code | finish_date | remaining_finish | planned_finish | remaining_late_finish | early_finish | late_finish | gis_id | resource_code_list | resource_name_list | ls | Join ID | Shape__Length | GlobalID
3 | 500 | schedule.specialist@aec.com | 28401 | 082182 | 12/31/21 | 48203 | 44205 | 28401 | PRE_MITIGATED | 44205 | 50205 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2021-12-31 | 2021-12-31 | 2022-01-28T08:00:00.+0000 | 80 | 0 | Pour Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2021-12-31 | 2022-01-28 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 160 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS1-1090 | 2022-01-13 | 2022-01-13 | 2022-01-13 | 2022-02-10 | 2022-01-13 | 2022-02-10 | PL1 | R2 | CIVIL | LS 1 | geo-polyline-1 | 13208.0721 | {5964C3EA-6C06-45FC-AF62-643B27BEE5C2}
3 | 400 | schedule.specialist@aec.com | 28401 | 082182 | 12/24/21 | 48203 | 44206 | 28401 | PRE_MITIGATED | 44206 | 50206 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2021-12-24 | 2021-12-24 | 2022-01-21T08:00:00.+0000 | 40 | 0 | Set Rebar Cage | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2021-12-24 | 2022-01-21 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 160 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS1-1100 | 2021-12-30 | 2021-12-30 | 2021-12-30 | 2022-01-27 | 2021-12-30 | 2022-01-27 | PL1 | R2 | CIVIL | LS 1 | geo-polyline-1 | 13208.0721 | {03453ABE-AAD0-4271-BBEC-E6A2FA6C5CA6}
1 | 135150 | schedule.specialist@aec.com | 28401 | 082182 | 03/03/22 | 48204 | 44208 | 28401 | PRE_MITIGATED | 44208 | 50208 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 40 | 0 | 40 | 0 | 0 | False | False | 1 | 2022-03-03 | 2022-03-03 | 2022-07-14T08:00:00.+0000 | 40 | 0 | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-03 | 2022-07-14 | NONE | 0 | 0 | 0 | 0 | 0 | 760 | 760 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | LS1-1010 | 2022-03-09 | 2022-03-09 | 2022-03-09 | 2022-07-20 | 2022-03-09 | 2022-07-20 | PL1 | R3 | Lightening Industries | LS 1 | geo-polyline-1 | 13208.0721 | {1DB676A2-36A2-4089-BA58-F2A56F3A5BF7}
2 | 135200 | schedule.specialist@aec.com | 28401 | 082182 | 02/17/22 | 48204 | 44209 | 28401 | PRE_MITIGATED | 44209 | 50209 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2022-02-17 | 2022-02-17 | 2022-06-30T08:00:00.+0000 | 80 | 0 | Install OPGW | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-17 | 2022-06-30 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 760 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 2 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS1-1020 | 2022-03-02 | 2022-03-02 | 2022-03-02 | 2022-07-13 | 2022-03-02 | 2022-07-13 | PL1 | R3 | Lightening Industries | LS 1 | geo-polyline-1 | 13208.0721 | {8472A7A4-5516-4CC2-8C24-8B2177DD6D50}
4 | 135250 | schedule.specialist@aec.com | 28401 | 082182 | 02/10/22 | 48204 | 44210 | 28401 | PRE_MITIGATED | 44210 | 50210 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 250 | 0 | 250 | 0 | 0 | False | False | 1 | 2022-02-10 | 2022-02-10 | 2022-06-23T08:00:00.+0000 | 40 | 0 | Pull, Sag and Clip Conductor | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-10 | 2022-06-23 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 760 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | LS1-1030 | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-06-29 | 2022-02-16 | 2022-06-29 | PL1 | R3 | Lightening Industries | LS 1 | geo-polyline-1 | 13208.0721 | {F4EBEE33-AAF8-4926-8369-E676A318F7A7}
1 | 135300 | schedule.specialist@aec.com | 28401 | 082182 | 01/20/22 | 48204 | 44211 | 28401 | PRE_MITIGATED | 44211 | 50211 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 200 | 0 | 200 | 0 | 0 | False | False | 1 | 2022-01-20 | 2022-01-20 | 2022-06-02T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-01-20 | 2022-06-02 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 760 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | LS1-1040 | 2022-01-26 | 2022-01-26 | 2022-01-26 | 2022-06-08 | 2022-01-26 | 2022-06-08 | PL1 | R3 | Lightening Industries | LS 1 | geo-polyline-1 | 13208.0721 | {2F5EF319-F7D0-4760-BB09-CAF9DA5F8D79}
1 | 136400 | schedule.specialist@aec.com | 28401 | 082182 | 03/25/22 | 46203 | 44212 | 28401 | PRE_MITIGATED | 44212 | 50212 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 120 | 0 | 120 | 0 | 0 | False | False | 1 | 2022-03-25 | 2022-03-25 | 2022-04-22T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-25 | 2022-04-22 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 160 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | LS65-1110 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2022-04-28 | 2022-03-31 | 2022-04-28 | PL6 | R2 | CIVIL | LS 6 | geo-polyline-6 | 8689.263 | {6CBC99B1-7406-474E-A5F4-8EAB834EBCCC}
4 | 136450 | schedule.specialist@aec.com | 28401 | 082182 | 03/04/22 | 46203 | 44213 | 28401 | PRE_MITIGATED | 44213 | 50213 | 2021-11-23 | Default Calendar | COST | 0 | 120 | 120 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-03-04 | 2022-03-04 | 2022-04-01T08:00:00.+0000 | 120 | 0 | ROW and Easement Clearing | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-04 | 2022-04-01 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 160 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS65-1120 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-04-21 | 2022-03-24 | 2022-04-21 | PL6 | R1, R2 | FICON, CIVIL | LS 6 | geo-polyline-6 | 8689.263 | {8DB76463-7292-4960-A201-97E8C04F4243}
3 | 136500 | schedule.specialist@aec.com | 28401 | 082182 | 04/01/22 | 46203 | 44214 | 28401 | PRE_MITIGATED | 44214 | 50214 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-04-01 | 2022-04-01 | 2022-04-29T08:00:00.+0000 | 40 | 0 | Drill Foundations | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-04-01 | 2022-04-29 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 160 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS65-1130 | 2022-04-07 | 2022-04-07 | 2022-04-07 | 2022-05-05 | 2022-04-07 | 2022-05-05 | PL6 | R2 | CIVIL | LS 6 | geo-polyline-6 | 8689.263 | {17452E0B-21FC-4159-81B2-1F36AB14D189}
3 | 136550 | schedule.specialist@aec.com | 28401 | 082182 | 04/08/22 | 46203 | 44215 | 28401 | PRE_MITIGATED | 44215 | 50215 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-04-08 | 2022-04-08 | 2022-05-06T08:00:00.+0000 | 40 | 0 | Set Rebar Cage | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-04-08 | 2022-05-06 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 160 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS65-1140 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-05-12 | 2022-04-14 | 2022-05-12 | PL6 | R2 | CIVIL | LS 6 | geo-polyline-6 | 8689.263 | {D61294DB-A727-481C-858B-27FFAF53FDEA}
3 | 136600 | schedule.specialist@aec.com | 28401 | 082182 | 04/15/22 | 46203 | 44216 | 28401 | PRE_MITIGATED | 44216 | 50216 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2022-04-15 | 2022-04-15 | 2022-05-13T08:00:00.+0000 | 80 | 0 | Pour Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-04-15 | 2022-05-13 | NONE | 0 | 0 | 0 | 0 | 0 | 160 | 160 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS65-1150 | 2022-04-28 | 2022-04-28 | 2022-04-28 | 2022-05-26 | 2022-04-28 | 2022-05-26 | PL6 | R2 | CIVIL | LS 6 | geo-polyline-6 | 8689.263 | {374857D1-E047-4B6C-AB95-76D157B63127}
1 | 136650 | schedule.specialist@aec.com | 28401 | 082182 | 03/03/22 | 46204 | 44217 | 28401 | PRE_MITIGATED | 44217 | 50217 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 40 | 0 | 40 | 0 | 0 | False | False | 1 | 2022-03-03 | 2022-03-03 | 2022-07-14T08:00:00.+0000 | 40 | 0 | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-03 | 2022-07-14 | NONE | 0 | 0 | 0 | 0 | 0 | 760 | 760 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | LS2-1010 | 2022-03-09 | 2022-03-09 | 2022-03-09 | 2022-07-20 | 2022-03-09 | 2022-07-20 | PL2 | R3 | Lightening Industries | LS 2 | geo-polyline-2 | 11681.654 | {04A1AE8E-A013-45AF-A2CF-503F23D240CE}
2 | 136700 | schedule.specialist@aec.com | 28401 | 082182 | 02/17/22 | 46204 | 44218 | 28401 | PRE_MITIGATED | 44218 | 50218 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2022-02-17 | 2022-02-17 | 2022-06-30T08:00:00.+0000 | 80 | 0 | Install OPGW | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-17 | 2022-06-30 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 760 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 2 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS2-1020 | 2022-03-02 | 2022-03-02 | 2022-03-02 | 2022-07-13 | 2022-03-02 | 2022-07-13 | PL2 | R3 | Lightening Industries | LS 2 | geo-polyline-2 | 11681.654 | {1F2A2D24-8732-4F9D-82F1-2E37530572DF}
4 | 136750 | schedule.specialist@aec.com | 28401 | 082182 | 02/10/22 | 46204 | 44219 | 28401 | PRE_MITIGATED | 44219 | 50219 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-02-10 | 2022-02-10 | 2022-06-23T08:00:00.+0000 | 40 | 0 | Pull, Sag and Clip Conductor | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-10 | 2022-06-23 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 760 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS2-1030 | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-06-29 | 2022-02-16 | 2022-06-29 | PL2 | R3 | Lightening Industries | LS 2 | geo-polyline-2 | 11681.654 | {AAF862AE-6BAB-4B70-BDE3-72D042C33CB2}
1 | 136800 | schedule.specialist@aec.com | 28401 | 082182 | 01/20/22 | 46204 | 44220 | 28401 | PRE_MITIGATED | 44220 | 50220 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 200 | 0 | 200 | 0 | 0 | False | False | 1 | 2022-01-20 | 2022-01-20 | 2022-06-02T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-01-20 | 2022-06-02 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 760 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | LS2-1040 | 2022-01-26 | 2022-01-26 | 2022-01-26 | 2022-06-08 | 2022-01-26 | 2022-06-08 | PL2 | R3 | Lightening Industries | LS 2 | geo-polyline-2 | 11681.654 | {9DC41972-E71A-4858-BDF2-D6D953A6B482}
3 | 136850 | schedule.specialist@aec.com | 28401 | 082182 | 01/27/22 | 46204 | 44221 | 28401 | PRE_MITIGATED | 44221 | 50221 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 500 | 0 | 500 | 0 | 0 | False | False | 1 | 2022-01-27 | 2022-01-27 | 2022-06-09T08:00:00.+0000 | 80 | 0 | Set Structures | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-01-27 | 2022-06-09 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 760 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | LS2-1050 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-06-22 | 2022-02-09 | 2022-06-22 | PL2 | R3 | Lightening Industries | LS 2 | geo-polyline-2 | 11681.654 | {CC97291D-FD67-43BB-9647-F0CB81A4BA75}
1 | 137650 | schedule.specialist@aec.com | 28401 | 082182 | 07/14/22 | 46205 | 44222 | 28401 | PRE_MITIGATED | 44222 | 50222 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 40 | 0 | 40 | 0 | 0 | True | False | 1 | 2022-07-14 | 2022-07-14 | 2022-07-14T08:00:00.+0000 | 40 | 0 | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-07-14 | 2022-07-14 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | LS6-1010 | 2022-07-20 | 2022-07-20 | 2022-07-20 | 2022-07-20 | 2022-07-20 | 2022-07-20 | PL6 | R3 | Lightening Industries | LS 6 | geo-polyline-6 | 8689.263 | {7F1E3E0A-22DA-49D7-9205-D4859B342854}
2 | 137700 | schedule.specialist@aec.com | 28401 | 082182 | 06/30/22 | 46205 | 44223 | 28401 | PRE_MITIGATED | 44223 | 50223 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | True | False | 1 | 2022-06-30 | 2022-06-30 | 2022-06-30T08:00:00.+0000 | 80 | 0 | Install OPGW | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-06-30 | 2022-06-30 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 2 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS6-1020 | 2022-07-13 | 2022-07-13 | 2022-07-13 | 2022-07-13 | 2022-07-13 | 2022-07-13 | PL6 | R3 | Lightening Industries | LS 6 | geo-polyline-6 | 8689.263 | {37918365-8C60-4731-9F00-0AC3986E6AB7}
4 | 137750 | schedule.specialist@aec.com | 28401 | 082182 | 06/23/22 | 46205 | 44224 | 28401 | PRE_MITIGATED | 44224 | 50224 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | True | False | 1 | 2022-06-23 | 2022-06-23 | 2022-06-23T08:00:00.+0000 | 40 | 0 | Pull, Sag and Clip Conductor | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-06-23 | 2022-06-23 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS6-1030 | 2022-06-29 | 2022-06-29 | 2022-06-29 | 2022-06-29 | 2022-06-29 | 2022-06-29 | PL6 | R3 | Lightening Industries | LS 6 | geo-polyline-6 | 8689.263 | {562AFD68-4CEF-4E8A-B63B-6D3C74FCA875}
1 | 137800 | schedule.specialist@aec.com | 28401 | 082182 | 06/02/22 | 46205 | 44225 | 28401 | PRE_MITIGATED | 44225 | 50225 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 200 | 0 | 200 | 0 | 0 | True | False | 1 | 2022-06-02 | 2022-06-02 | 2022-06-02T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-06-02 | 2022-06-02 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | LS6-1040 | 2022-06-08 | 2022-06-08 | 2022-06-08 | 2022-06-08 | 2022-06-08 | 2022-06-08 | PL6 | R3 | Lightening Industries | LS 6 | geo-polyline-6 | 8689.263 | {3ACC16D1-2991-4155-B37B-AC9610FB3E0D}
3 | 137850 | schedule.specialist@aec.com | 28401 | 082182 | 06/09/22 | 46205 | 44226 | 28401 | PRE_MITIGATED | 44226 | 50226 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | True | False | 1 | 2022-06-09 | 2022-06-09 | 2022-06-09T08:00:00.+0000 | 80 | 0 | Set Structures | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-06-09 | 2022-06-09 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS6-1050 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | PL6 | R3 | Lightening Industries | LS 6 | geo-polyline-6 | 8689.263 | {1897AB0C-C271-413C-BB91-F3022F655D9E}
3 | 300 | schedule.specialist@aec.com | 28401 | 082182 | 12/17/21 | 48203 | 44301 | 28401 | PRE_MITIGATED | 44301 | 50301 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2021-12-17 | 2021-12-17 | 2022-01-14T08:00:00.+0000 | 40 | 0 | Drill Foundations | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2021-12-17 | 2022-01-14 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 160 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS1-1080 | 2021-12-23 | 2021-12-23 | 2021-12-23 | 2022-01-20 | 2021-12-23 | 2022-01-20 | PL1 | R2 | CIVIL | LS 1 | geo-polyline-1 | 13208.0721 | {2C42D0E6-A781-4D34-8F14-F1641401F6A9}
3 | 135350 | schedule.specialist@aec.com | 28401 | 082182 | 01/27/22 | 48204 | 44302 | 28401 | PRE_MITIGATED | 44302 | 50302 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 500 | 0 | 500 | 0 | 0 | False | False | 1 | 2022-01-27 | 2022-01-27 | 2022-06-09T08:00:00.+0000 | 80 | 0 | Set Structures | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-01-27 | 2022-06-09 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 760 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | LS1-1050 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-06-22 | 2022-02-09 | 2022-06-22 | PL1 | R3 | Lightening Industries | LS 1 | geo-polyline-1 | 13208.0721 | {6083D507-8449-4C67-827E-FED9BA5BD39B}
1 | 135650 | schedule.specialist@aec.com | 28401 | 082182 | 01/21/22 | 48305 | 44303 | 28401 | PRE_MITIGATED | 44303 | 50303 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 120 | 0 | 120 | 0 | 0 | False | False | 1 | 2022-01-21 | 2022-01-21 | 2022-02-04T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-01-21 | 2022-02-04 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 80 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | LS3-1110 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-02-10 | 2022-01-27 | 2022-02-10 | PL3 | R2 | CIVIL | LS 3 | geo-polyline-3 | 5272.9579 | {6B92A84F-4A7C-4454-94F0-D974272CCA0E}
4 | 135700 | schedule.specialist@aec.com | 28401 | 082182 | 12/31/21 | 48305 | 44304 | 28401 | PRE_MITIGATED | 44304 | 50304 | 2021-11-23 | Default Calendar | COST | 0 | 120 | 120 | 1 | 240 | 0 | 240 | 0 | 0 | True | False | 1 | 2021-12-31 | 2021-12-31 | 2021-12-31T08:00:00.+0000 | 120 | 0 | ROW and Easement Clearing | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2021-12-31 | 2021-12-31 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS3-1120 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-20 | PL3 | R1, R2 | FICON, CIVIL | LS 3 | geo-polyline-3 | 5272.9579 | {FB2A140F-AEBD-4325-B72C-6868BF92E268}
3 | 135750 | schedule.specialist@aec.com | 28401 | 082182 | 01/28/22 | 48305 | 44305 | 28401 | PRE_MITIGATED | 44305 | 50305 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-01-28 | 2022-01-28 | 2022-02-11T08:00:00.+0000 | 40 | 0 | Drill Foundations | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-01-28 | 2022-02-11 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 80 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS3-1130 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-17 | 2022-02-03 | 2022-02-17 | PL3 | R2 | CIVIL | LS 3 | geo-polyline-3 | 5272.9579 | {1A6967D6-7C23-4BEC-8727-64A05717F37C}
3 | 135800 | schedule.specialist@aec.com | 28401 | 082182 | 02/04/22 | 48305 | 44306 | 28401 | PRE_MITIGATED | 44306 | 50306 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-02-04 | 2022-02-04 | 2022-02-18T08:00:00.+0000 | 40 | 0 | Set Rebar Cage | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-04 | 2022-02-18 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 80 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS3-1140 | 2022-02-10 | 2022-02-10 | 2022-02-10 | 2022-02-24 | 2022-02-10 | 2022-02-24 | PL3 | R2 | CIVIL | LS 3 | geo-polyline-3 | 5272.9579 | {273AD227-3A31-49F9-B186-651E6EBA29E9}
3 | 135850 | schedule.specialist@aec.com | 28401 | 082182 | 02/11/22 | 48305 | 44307 | 28401 | PRE_MITIGATED | 44307 | 50307 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2022-02-11 | 2022-02-11 | 2022-02-25T08:00:00.+0000 | 80 | 0 | Pour Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-11 | 2022-02-25 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 80 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS3-1150 | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-03-10 | 2022-02-24 | 2022-03-10 | PL3 | R2 | CIVIL | LS 3 | geo-polyline-3 | 5272.9579 | {55A415A1-3B67-4761-92A4-0EC2EDC3D3FE}
1 | 137400 | schedule.specialist@aec.com | 28401 | 082182 | 05/26/22 | 48306 | 44308 | 28401 | PRE_MITIGATED | 44308 | 50308 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 40 | 0 | 40 | 0 | 0 | True | False | 1 | 2022-05-26 | 2022-05-26 | 2022-05-26T08:00:00.+0000 | 40 | 0 | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-05-26 | 2022-05-26 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | LS5-1010 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | PL5 | R3 | Lightening Industries | LS 5 | geo-polyline-5 | 5606.7564 | {094B89F5-3C13-424A-AC19-0418246DA885}
2 | 137450 | schedule.specialist@aec.com | 28401 | 082182 | 05/12/22 | 48306 | 44309 | 28401 | PRE_MITIGATED | 44309 | 50309 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | True | False | 1 | 2022-05-12 | 2022-05-12 | 2022-05-12T08:00:00.+0000 | 80 | 0 | Install OPGW | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-05-12 | 2022-05-12 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 2 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS5-1020 | 2022-05-25 | 2022-05-25 | 2022-05-25 | 2022-05-25 | 2022-05-25 | 2022-05-25 | PL5 | R3 | Lightening Industries | LS 5 | geo-polyline-5 | 5606.7564 | {FC420520-D2E4-4FF2-9370-48D2C1E5B884}
4 | 137500 | schedule.specialist@aec.com | 28401 | 082182 | 05/05/22 | 48306 | 44310 | 28401 | PRE_MITIGATED | 44310 | 50310 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | True | False | 1 | 2022-05-05 | 2022-05-05 | 2022-05-05T08:00:00.+0000 | 40 | 0 | Pull, Sag and Clip Conductor | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-05-05 | 2022-05-05 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS5-1030 | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-11 | PL5 | R3 | Lightening Industries | LS 5 | geo-polyline-5 | 5606.7564 | {5E678351-7F8B-43AB-9CE5-4269ABB6B41E}
1 | 137550 | schedule.specialist@aec.com | 28401 | 082182 | 04/14/22 | 48306 | 44311 | 28401 | PRE_MITIGATED | 44311 | 50311 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 200 | 0 | 200 | 0 | 0 | True | False | 1 | 2022-04-14 | 2022-04-14 | 2022-04-14T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-04-14 | 2022-04-14 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | LS5-1040 | 2022-04-20 | 2022-04-20 | 2022-04-20 | 2022-04-20 | 2022-04-20 | 2022-04-20 | PL5 | R3 | Lightening Industries | LS 5 | geo-polyline-5 | 5606.7564 | {4AC70053-E616-402C-8291-44C08BB9962B}
3 | 137600 | schedule.specialist@aec.com | 28401 | 082182 | 04/21/22 | 48306 | 44312 | 28401 | PRE_MITIGATED | 44312 | 50312 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | True | False | 1 | 2022-04-21 | 2022-04-21 | 2022-04-21T08:00:00.+0000 | 80 | 0 | Set Structures | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-04-21 | 2022-04-21 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS5-1050 | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2022-05-04 | PL5 | R3 | Lightening Industries | LS 5 | geo-polyline-5 | 5606.7564 | {F9C22039-4D9D-4D4C-8B53-49E15ACE480B}
4 | 200 | schedule.specialist@aec.com | 28401 | 082182 | 12/06/21 | 48203 | 46203 | 28401 | PRE_MITIGATED | 46203 | 52203 | 2021-11-23 | Default Calendar | COST | 0 | 32 | 32 | 1 | 375 | 0 | 375 | 0 | 0 | True | False | 1 | 2021-12-06 | 2021-12-06 | 2021-12-06T08:00:00.+0000 | 32 | 0 | ROW and Easement Clearing | 0 | 0 | 14416.6667 | -14416.6667 | 0 | 0 | 43250 | 43250 | 0 | 0 | 0 | 0 | 43250 | 43250 | 0 | 43250 | 43250 | 0 | 0 | 0 | 0 | 43250 | 43250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43250 | 43250 | 0 | 0 | 0 | 0 | 43250 | 43250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43250 | 43250 | 14416.6667 | 0 | -14416.6667 | 0 | 0 | 43250 | 43250 | 43250 | 43250 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2021-12-06 | 2021-12-06 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 375 | 125 | -125 | -1 | 0 | 0 | 375 | 375 | 0 | LS1-1060 | 2021-12-09 | 2021-12-09 | 2021-12-09 | 2021-12-09 | 2021-12-09 | 2021-12-09 | PL1 | R1, R2 | FICON, CIVIL | LS 1 | geo-polyline-1 | 13208.0721 | {9F865443-0F7C-41C1-9CB9-287BBE4E95C6}
1 | 100 | schedule.specialist@aec.com | 28401 | 082182 | 12/10/21 | 48203 | 46204 | 28401 | PRE_MITIGATED | 46204 | 52204 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 120 | 0 | 120 | 0 | 0 | False | False | 1 | 2021-12-10 | 2021-12-10 | 2022-01-07T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2021-12-10 | 2022-01-07 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 160 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | LS1-1070 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2022-01-13 | 2021-12-16 | 2022-01-13 | PL1 | R2 | CIVIL | LS 1 | geo-polyline-1 | 13208.0721 | {9FA0CB60-AB2C-4F4E-BDCF-4A5C029E8D7F}
1 | 135400 | schedule.specialist@aec.com | 28401 | 082182 | 12/31/21 | 48205 | 46205 | 28401 | PRE_MITIGATED | 46205 | 52205 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 120 | 0 | 120 | 0 | 0 | False | False | 1 | 2021-12-31 | 2021-12-31 | 2022-01-21T08:00:00.+0000 | 40 | 0 | Stage Material Structures 16-30 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2021-12-31 | 2022-01-21 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 120 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | LS2-1070 | 2022-01-06 | 2022-01-06 | 2022-01-06 | 2022-01-27 | 2022-01-06 | 2022-01-27 | PL2 | R2 | CIVIL | LS 2 | geo-polyline-2 | 11681.654 | {9402DC8E-5C30-450C-9E92-1AA4E3FB21AA}
4 | 135450 | schedule.specialist@aec.com | 28401 | 082182 | 12/10/21 | 48205 | 46206 | 28401 | PRE_MITIGATED | 46206 | 52206 | 2021-11-23 | Default Calendar | COST | 0 | 120 | 120 | 1 | 370 | 0 | 370 | 0 | 0 | True | False | 1 | 2021-12-10 | 2021-12-10 | 2021-12-10T08:00:00.+0000 | 120 | 0 | ROW and Easement Clearing | 0 | 0 | 0 | 0 | 0 | 0 | 42700 | 42700 | 0 | 0 | 0 | 0 | 42700 | 42700 | 0 | 42700 | 42700 | 0 | 0 | 0 | 0 | 42700 | 42700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42700 | 42700 | 0 | 0 | 0 | 0 | 42700 | 42700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42700 | 42700 | 0 | 0 | 0 | 0 | 0 | 42700 | 42700 | 42700 | 42700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2021-12-10 | 2021-12-10 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 370 | 0 | 0 | 0 | 0 | 0 | 370 | 370 | 0 | LS2-1060 | 2021-12-30 | 2021-12-30 | 2021-12-30 | 2021-12-30 | 2021-12-30 | 2021-12-30 | PL2 | R1, R2 | FICON, CIVIL | LS 2 | geo-polyline-2 | 11681.654 | {0039B878-34DB-4F64-9DA8-B8D2134D2987}
3 | 135500 | schedule.specialist@aec.com | 28401 | 082182 | 01/07/22 | 48205 | 46207 | 28401 | PRE_MITIGATED | 46207 | 52207 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-01-07 | 2022-01-07 | 2022-01-28T08:00:00.+0000 | 40 | 0 | Drill Foundations | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-01-07 | 2022-01-28 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 120 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS2-1080 | 2022-01-13 | 2022-01-13 | 2022-01-13 | 2022-02-03 | 2022-01-13 | 2022-02-03 | PL2 | R2 | CIVIL | LS 2 | geo-polyline-2 | 11681.654 | {A6C4ED0C-287C-40F0-8C29-A6E162F3B772}
3 | 135550 | schedule.specialist@aec.com | 28401 | 082182 | 01/14/22 | 48205 | 46208 | 28401 | PRE_MITIGATED | 46208 | 52208 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-01-14 | 2022-01-14 | 2022-02-04T08:00:00.+0000 | 40 | 0 | Set Rebar Cage | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-01-14 | 2022-02-04 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 120 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS2-1100 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-02-10 | 2022-01-20 | 2022-02-10 | PL2 | R2 | CIVIL | LS 2 | geo-polyline-2 | 11681.654 | {B1517A11-3036-4E10-BABF-9E90637CA4CE}
3 | 135600 | schedule.specialist@aec.com | 28401 | 082182 | 01/21/22 | 48205 | 46209 | 28401 | PRE_MITIGATED | 46209 | 52209 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2022-01-21 | 2022-01-21 | 2022-02-11T08:00:00.+0000 | 80 | 0 | Pour Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-01-21 | 2022-02-11 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 120 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS2-1090 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-24 | 2022-02-03 | 2022-02-24 | PL2 | R2 | CIVIL | LS 2 | geo-polyline-2 | 11681.654 | {04FEAF24-E925-453C-B686-AE40C5EE7E20}
1 | 135900 | schedule.specialist@aec.com | 28401 | 082182 | 02/11/22 | 48206 | 46210 | 28401 | PRE_MITIGATED | 46210 | 52210 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 120 | 0 | 120 | 0 | 0 | False | False | 1 | 2022-02-11 | 2022-02-11 | 2022-02-18T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-11 | 2022-02-18 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 40 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | LS4-1110 | 2022-02-17 | 2022-02-17 | 2022-02-17 | 2022-02-24 | 2022-02-17 | 2022-02-24 | PL4 | R2 | CIVIL | LS 4 | geo-polyline-4 | 9571.8612 | {BDBBBD47-B5FB-48BB-92D6-BCF7CE78D6B1}
4 | 135950 | schedule.specialist@aec.com | 28401 | 082182 | 01/21/22 | 48206 | 46211 | 28401 | PRE_MITIGATED | 46211 | 52211 | 2021-11-23 | Default Calendar | COST | 0 | 120 | 120 | 1 | 240 | 0 | 240 | 0 | 0 | True | False | 1 | 2022-01-21 | 2022-01-21 | 2022-01-21T08:00:00.+0000 | 120 | 0 | ROW and Easement Clearing | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-01-21 | 2022-01-21 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS4-1120 | 2022-02-10 | 2022-02-10 | 2022-02-10 | 2022-02-10 | 2022-02-10 | 2022-02-10 | PL4 | R1, R2 | FICON, CIVIL | LS 4 | geo-polyline-4 | 9571.8612 | {3A94DD21-1374-4F1E-9903-360139DCCA0F}
3 | 136000 | schedule.specialist@aec.com | 28401 | 082182 | 02/18/22 | 48206 | 46212 | 28401 | PRE_MITIGATED | 46212 | 52212 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-02-18 | 2022-02-18 | 2022-02-25T08:00:00.+0000 | 40 | 0 | Drill Foundations | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-18 | 2022-02-25 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 40 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS4-1130 | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-03-03 | 2022-02-24 | 2022-03-03 | PL4 | R2 | CIVIL | LS 4 | geo-polyline-4 | 9571.8612 | {18FA2E79-796C-48A6-ACBE-2BC891C62A08}
3 | 136050 | schedule.specialist@aec.com | 28401 | 082182 | 02/25/22 | 48206 | 46213 | 28401 | PRE_MITIGATED | 46213 | 52213 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-02-25 | 2022-02-25 | 2022-03-04T08:00:00.+0000 | 40 | 0 | Set Rebar Cage | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-25 | 2022-03-04 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 40 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS4-1140 | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2022-03-10 | 2022-03-03 | 2022-03-10 | PL4 | R2 | CIVIL | LS 4 | geo-polyline-4 | 9571.8612 | {C03C4162-7E3E-421A-A1FF-C978BDFA845E}
3 | 136100 | schedule.specialist@aec.com | 28401 | 082182 | 03/04/22 | 48206 | 46214 | 28401 | PRE_MITIGATED | 46214 | 52214 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2022-03-04 | 2022-03-04 | 2022-03-11T08:00:00.+0000 | 80 | 0 | Pour Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-04 | 2022-03-11 | NONE | 0 | 0 | 0 | 0 | 0 | 40 | 40 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS4-1150 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-24 | 2022-03-17 | 2022-03-24 | PL4 | R2 | CIVIL | LS 4 | geo-polyline-4 | 9571.8612 | {581253B2-D284-49F9-AAD6-B77F9DACA37D}
1 | 136150 | schedule.specialist@aec.com | 28401 | 082182 | 03/04/22 | 48208 | 46215 | 28401 | PRE_MITIGATED | 46215 | 52215 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 120 | 0 | 120 | 0 | 0 | True | False | 1 | 2022-03-04 | 2022-03-04 | 2022-03-04T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-03-04 | 2022-03-04 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | LS5-1110 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-10 | PL5 | R2 | CIVIL | LS 5 | geo-polyline-5 | 5606.7564 | {22DEDC95-F8D5-466C-A85F-43E339445A8B}
4 | 136200 | schedule.specialist@aec.com | 28401 | 082182 | 02/11/22 | 48208 | 46216 | 28401 | PRE_MITIGATED | 46216 | 52216 | 2021-11-23 | Default Calendar | COST | 0 | 120 | 120 | 1 | 240 | 0 | 240 | 0 | 0 | True | False | 1 | 2022-02-11 | 2022-02-11 | 2022-02-11T08:00:00.+0000 | 120 | 0 | ROW and Easement Clearing | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 27600 | 27600 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-02-11 | 2022-02-11 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS5-1120 | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2022-03-03 | PL5 | R1, R2 | FICON, CIVIL | LS 5 | geo-polyline-5 | 5606.7564 | {1C886636-0917-43E3-864B-46E3169F27FC}
3 | 136250 | schedule.specialist@aec.com | 28401 | 082182 | 03/11/22 | 48208 | 46217 | 28401 | PRE_MITIGATED | 46217 | 52217 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | True | False | 1 | 2022-03-11 | 2022-03-11 | 2022-03-11T08:00:00.+0000 | 40 | 0 | Drill Foundations | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-03-11 | 2022-03-11 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS5-1130 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-17 | PL5 | R2 | CIVIL | LS 5 | geo-polyline-5 | 5606.7564 | {2DDF52B7-28A2-4134-8196-A847B5FAB647}
3 | 136300 | schedule.specialist@aec.com | 28401 | 082182 | 03/18/22 | 48208 | 46218 | 28401 | PRE_MITIGATED | 46218 | 52218 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | True | False | 1 | 2022-03-18 | 2022-03-18 | 2022-03-18T08:00:00.+0000 | 40 | 0 | Set Rebar Cage | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 26400 | 26400 | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-03-18 | 2022-03-18 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS5-1140 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | PL5 | R2 | CIVIL | LS 5 | geo-polyline-5 | 5606.7564 | {48B97689-C824-4543-A08A-16F23E17A6BB}
3 | 136350 | schedule.specialist@aec.com | 28401 | 082182 | 03/25/22 | 48208 | 46219 | 28401 | PRE_MITIGATED | 46219 | 52219 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | True | False | 1 | 2022-03-25 | 2022-03-25 | 2022-03-25T08:00:00.+0000 | 80 | 0 | Pour Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | True | 0 | 0 | 2022-03-25 | 2022-03-25 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS5-1150 | 2022-04-07 | 2022-04-07 | 2022-04-07 | 2022-04-07 | 2022-04-07 | 2022-04-07 | PL5 | R2 | CIVIL | LS 5 | geo-polyline-5 | 5606.7564 | {E16BC79C-B117-453D-8560-2E5B7C67637B}
1 | 136900 | schedule.specialist@aec.com | 28401 | 082182 | 03/24/22 | 48209 | 46220 | 28401 | PRE_MITIGATED | 46220 | 52220 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 40 | 0 | 40 | 0 | 0 | False | False | 1 | 2022-03-24 | 2022-03-24 | 2022-07-14T08:00:00.+0000 | 40 | 0 | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-24 | 2022-07-14 | NONE | 0 | 0 | 0 | 0 | 0 | 640 | 640 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | LS3-1010 | 2022-03-30 | 2022-03-30 | 2022-03-30 | 2022-07-20 | 2022-03-30 | 2022-07-20 | PL3 | R3 | Lightening Industries | LS 3 | geo-polyline-3 | 5272.9579 | {6549B26A-CE22-497D-B01D-FA501E0BD8E5}
2 | 136950 | schedule.specialist@aec.com | 28401 | 082182 | 03/10/22 | 48209 | 46221 | 28401 | PRE_MITIGATED | 46221 | 52221 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2022-03-10 | 2022-03-10 | 2022-06-30T08:00:00.+0000 | 80 | 0 | Install OPGW | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-10 | 2022-06-30 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 640 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 2 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS3-1020 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-07-13 | 2022-03-23 | 2022-07-13 | PL3 | R3 | Lightening Industries | LS 3 | geo-polyline-3 | 5272.9579 | {F36754CC-56E2-47E7-B7D2-552761E3278E}
4 | 137000 | schedule.specialist@aec.com | 28401 | 082182 | 03/03/22 | 48209 | 46222 | 28401 | PRE_MITIGATED | 46222 | 52222 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-03-03 | 2022-03-03 | 2022-06-23T08:00:00.+0000 | 40 | 0 | Pull, Sag and Clip Conductor | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-03 | 2022-06-23 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 640 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS3-1030 | 2022-03-09 | 2022-03-09 | 2022-03-09 | 2022-06-29 | 2022-03-09 | 2022-06-29 | PL3 | R3 | Lightening Industries | LS 3 | geo-polyline-3 | 5272.9579 | {3DB574A2-B399-40AD-ACCB-E02E71363BB7}
1 | 137050 | schedule.specialist@aec.com | 28401 | 082182 | 02/10/22 | 48209 | 46223 | 28401 | PRE_MITIGATED | 46223 | 52223 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 200 | 0 | 200 | 0 | 0 | False | False | 1 | 2022-02-10 | 2022-02-10 | 2022-06-02T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-10 | 2022-06-02 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 640 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | LS3-1040 | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-06-08 | 2022-02-16 | 2022-06-08 | PL3 | R3 | Lightening Industries | LS 3 | geo-polyline-3 | 5272.9579 | {21AA85DB-DEE3-41FE-A0F9-831F029A6F9C}
3 | 137100 | schedule.specialist@aec.com | 28401 | 082182 | 02/17/22 | 48209 | 46224 | 28401 | PRE_MITIGATED | 46224 | 52224 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2022-02-17 | 2022-02-17 | 2022-06-09T08:00:00.+0000 | 80 | 0 | Set Structures | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-02-17 | 2022-06-09 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 640 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS3-1050 | 2022-03-02 | 2022-03-02 | 2022-03-02 | 2022-06-22 | 2022-03-02 | 2022-06-22 | PL3 | R3 | Lightening Industries | LS 3 | geo-polyline-3 | 5272.9579 | {322B4E3E-87BB-46AE-B465-B5E0C4077CF3}
1 | 137150 | schedule.specialist@aec.com | 28401 | 082182 | 04/14/22 | 48210 | 46225 | 28401 | PRE_MITIGATED | 46225 | 52225 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 40 | 0 | 40 | 0 | 0 | False | False | 1 | 2022-04-14 | 2022-04-14 | 2022-07-14T08:00:00.+0000 | 40 | 0 | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-04-14 | 2022-07-14 | NONE | 0 | 0 | 0 | 0 | 0 | 520 | 520 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | LS4-1010 | 2022-04-20 | 2022-04-20 | 2022-04-20 | 2022-07-20 | 2022-04-20 | 2022-07-20 | PL4 | R3 | Lightening Industries | LS 4 | geo-polyline-4 | 9571.8612 | {015785C7-DCEB-4787-B4CB-9ECF3D0B8A52}
2 | 137200 | schedule.specialist@aec.com | 28401 | 082182 | 03/31/22 | 48210 | 46226 | 28401 | PRE_MITIGATED | 46226 | 52226 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2022-03-31 | 2022-03-31 | 2022-06-30T08:00:00.+0000 | 80 | 0 | Install OPGW | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-31 | 2022-06-30 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 520 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 2 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS4-1020 | 2022-04-13 | 2022-04-13 | 2022-04-13 | 2022-07-13 | 2022-04-13 | 2022-07-13 | PL4 | R3 | Lightening Industries | LS 4 | geo-polyline-4 | 9571.8612 | {E9666A30-A1CB-48CE-9095-DA287C853474}
4 | 137250 | schedule.specialist@aec.com | 28401 | 082182 | 03/24/22 | 48210 | 46227 | 28401 | PRE_MITIGATED | 46227 | 52227 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 240 | 0 | 240 | 0 | 0 | False | False | 1 | 2022-03-24 | 2022-03-24 | 2022-06-23T08:00:00.+0000 | 40 | 0 | Pull, Sag and Clip Conductor | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-24 | 2022-06-23 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 520 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 4 | 0 | 0 | 0 | False | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | LS4-1030 | 2022-03-30 | 2022-03-30 | 2022-03-30 | 2022-06-29 | 2022-03-30 | 2022-06-29 | PL4 | R3 | Lightening Industries | LS 4 | geo-polyline-4 | 9571.8612 | {1E7091B7-8488-4AD5-BC2A-9FE84B54E5B7}
1 | 137300 | schedule.specialist@aec.com | 28401 | 082182 | 03/03/22 | 48210 | 46228 | 28401 | PRE_MITIGATED | 46228 | 52228 | 2021-11-23 | Default Calendar | COST | 0 | 40 | 40 | 1 | 200 | 0 | 200 | 0 | 0 | False | False | 1 | 2022-03-03 | 2022-03-03 | 2022-06-02T08:00:00.+0000 | 40 | 0 | Stage Material | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-03 | 2022-06-02 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 520 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 1 | 0 | 0 | 0 | False | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | LS4-1040 | 2022-03-09 | 2022-03-09 | 2022-03-09 | 2022-06-08 | 2022-03-09 | 2022-06-08 | PL4 | R3 | Lightening Industries | LS 4 | geo-polyline-4 | 9571.8612 | {7DC9FDF0-1DFA-46CF-BA0F-19065D049FA7}
3 | 137350 | schedule.specialist@aec.com | 28401 | 082182 | 03/10/22 | 48210 | 46229 | 28401 | PRE_MITIGATED | 46229 | 52229 | 2021-11-23 | Default Calendar | COST | 0 | 80 | 80 | 1 | 480 | 0 | 480 | 0 | 0 | False | False | 1 | 2022-03-10 | 2022-03-10 | 2022-06-09T08:00:00.+0000 | 80 | 0 | Set Structures | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | False | 0 | 0 | 2022-03-10 | 2022-06-09 | NONE | 0 | 0 | 0 | 0 | 0 | 0 | 520 | NOT_STARTED | PHYSICAL | 0 | FIXED_DURATION_AND_UNITS | ACTIVITY | NORMAL | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | ALL_WITHIN | BOTH_NOT_COMPLETE | False | 3 | 0 | 0 | 0 | False | 480 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | LS4-1050 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-06-22 | 2022-03-23 | 2022-06-22 | PL4 | R3 | Lightening Industries | LS 4 | geo-polyline-4 | 9571.8612 | {D925C8DB-B644-4980-9AF3-9EF17843BDC9}